Summary of Communication Trail – Email_03

This email thread relates to project governance, reporting requirements, and focal point alignment for the SDV New Buildings / FMP-2277 – PRFEBA Buildings Package (Mess Hall & G+1 Office Building) involving Altrad Babcock, Mecton, and OBG.

1. Change in Project Focal Point (Altrad Babcock)

- Abdul Basit (Project Manager, Altrad Babcock) formally notifies that Raheel Babar has been appointed as the site focal point for all subcontract operational performance.

- From that point onward, Raheel is to be the primary interface with Mecton / OBG for all correspondence and coordination.

2. Comprehensive Reporting Directive Issued

- Raheel Babar follows up with a formal instruction to Ashwin John (Mecton/OBG) requiring submission of a detailed and structured project status report.

- The request reflects:

  - Accelerated project schedule

  - High interface risk due to a live gas plant environment

  - Need for full technical and execution visibility

Reporting scope explicitly covers:

- Engineering & technical documentation (IFC drawings, MS, ITPs, TQs, compliance with DEL Energy standards)

- Procurement & material inspection status (MARs, POs, inspections, ETAs)

- Prefabrication scope under OBG (fabrication, NDT, painting, dispatch, site installation strategy)

- Civil foundations readiness and interface issues

- Construction execution strategy, manpower, equipment, lifting, logistics, and HSE

- Mandatory daily progress reporting

- Identification of pending approvals and interface constraints requiring Altrad / DEL Energy intervention

Deadline:

- Initial consolidated report by COB 8 October 2025, followed by daily DPRs thereafter.

3. Mecton / OBG Focal Point Clarification

- Don Saman (GM – Mecton Al Laith) responds to clarify internal responsibilities:

  - Biju Jose (assigned PM) is on leave and expected to return by 20 October.

  - Ashwin John is designated as the temporary focal point from the Mecton / OBG side until Biju’s return.

Overall Context & Implications

- The exchange signals a tightening of project controls by Altrad Babcock.

- Emphasis is placed on discipline in reporting, interface management, and execution transparency.

- The communication formally aligns who is accountable on both sides, reducing ambiguity during a critical execution phase.

- The tone reflects schedule sensitivity and heightened oversight, typical of work within a live gas plant environment.

If you’d like, I can also:

- Extract action items and risks from this trail

- Convert the reporting requirements into a ready-to-use DPR / status report template

- Map this email against contractual obligations or escalation exposure