Below is a clear, management-level summary of the communication trail contained in Email_01, presented chronologically and focused on issue evolution, responsibilities, and current status.

1. Background & Initial Submission

- 02 Jan 2025 – Mecton submitted the structural design calculations to Altrad Babcock.

- 11 Jan 2025 – Altrad forwarded the submission to Dolphin Energy (DEL) for review.

- For several months, the design remained under review, while site activities progressed based on the submitted (not approved) design, following Altrad/DEL directions.

This prolonged review period later became a core point of contention.

2. Design Resubmission & Clarifications (Early October 2025)

- 08 Oct 2025 – Ashwin John (Mecton) formally resubmitted updated structural drawings and transmittals for the Mess Hall / Portacabin structure, stating that:

  - Previous Altrad comments had been incorporated.

  - Documents were submitted for review and approval.

3. Engineering Concerns Raised by Altrad

- 09 Oct 2025 – Internal Altrad communication (Thadathilshaji → Irfan Sheikh) highlighted technical gaps and instructed QA/QC to formally raise them with Mecton:

  - Missing Buckling Analysis for slender compression members.

  - Purlin load checks not explicitly analysed, despite being included in SDL.

  - Request for drawings + design calculations to address these points.

- These comments were then formally forwarded to Mecton by Irfan Sheikh.

4. Escalation by Altrad – “Serious Concern”

- 11 Oct 2025 – Raheel Babar (Lead Subcontracts, Altrad) escalated the matter, stating:

  - The email raises a “serious concern about engineering design”.

  - Requested immediate response and resolution.

This marked a shift from routine review comments to formal concern escalation.

5. Mecton’s Position & Operational Impact

- 11–19 Oct 2025 – Ashwin John (Mecton) responded, highlighting:

  - The design had been with Altrad/DEL for ~9 months without approval.

  - 84% of drawings were still pending approval.

  - Foundation works and cabin frame fabrication had already been executed per instructions.

  - Continuing without approval poses major project risks.

- Due to the unresolved design issue, cabin shifting activities were put on hold as instructed by Altrad.

- Mecton formally requested confirmation on when work could resume.

6. DEL Comments & Request for Resolution

- 19 Oct 2025 – Abdul Basit (Altrad) transmitted DEL’s consolidated comments, requesting:

  - Resolution of comments at the earliest.

- 22 Oct 2025 – Basit clarified:

  - DEL comments apply to the overall structural design.

  - A technical discussion could be arranged if required.

7. Management-Level Intervention (Mecton)

- 22 Oct 2025 – Don Saman (General Manager, Mecton) responded firmly:

  - It is Altrad’s decision whether to arrange a technical meeting.

  - All comments must be raised in one consolidated set, not piecemeal.

  - Once clarified, no further queries should remain.

- In a later, stronger response, Don Saman noted:

  - Altrad has held the engineering package for ~8 months.

  - The trailing comments appeared reactive and inconsistent.

  - Directed Ashwin to sit jointly with Altrad and OBG design/production teams to close all issues in one session.

8. Current Status (as per trail)

- Key unresolved items:

  - Buckling analysis.

  - Explicit purlin structural checks.

  - Final alignment between submitted design, DEL comments, and execution already done on site.

- Operational impact:

  - Cabin shifting works on hold.

  - Commercial and schedule risk due to late design clarification.

- Next logical step:

  - A single, structured technical workshop involving Altrad, DEL (if required), Mecton, and OBG, closing all comments in one cycle and enabling formal approval and work resumption.

Executive One-Line Summary

The email trail documents a prolonged design approval delay (≈9 months), late-stage escalation of structural design concerns by Altrad/DEL, suspension of site activities, and Mecton’s firm request to consolidate and resolve all technical queries in one coordinated technical session to unlock approvals and resume work.

If you want, I can next:

- Extract all DEL technical comments into a single action-tracking table, or

- Draft a formal closure email / meeting request aligned with this trail.