Below is a concise, structured summary of the Email_04 communication trail, focusing on intent, responsibilities, and outcomes.

Summary of Communication Trail – Email_04

1. Purpose of the Email Thread

The email chain centers on establishing project focal points and enforcing structured reporting requirements for the SDV New Buildings / FMP-2277 – PRFEBA Buildings Package (Mess Hall and G+1 Office Building) within a live gas plant environment .

2. Key Participants & Roles

- Altrad Babcock

  - Abdul Basit – Project Manager

  - Raheel Babar – Newly appointed site focal point for subcontract operational performance

- Mecton / OBG

  - Don Saman – General Manager

  - Biju Jose – Project Manager (on leave)

  - Ashwin John – Interim project focal point during PM’s absence

3. Chronological Flow of Communication

a. Appointment of Altrad Site Focal (Initiation)

- Abdul Basit formally informs all parties that Raheel Babar is appointed as the single point of contact for all subcontract-related operational coordination with Mecton/OBG.

b. Formal Reporting Directive

- Raheel Babar issues a detailed and directive instruction to Mecton/OBG requesting:

  - A comprehensive consolidated project status report

  - Mandatory daily progress reporting

  - Full transparency across engineering, procurement, fabrication, civil works, construction execution, and HSE

- A hard deadline is set:

  - Initial consolidated report by COB 8 October 2025

  - Daily DPRs thereafter

c. Scope and Expectations Clearly Defined
The requested report must cover:

- Engineering deliverables (IFC drawings, method statements, ITPs, TQs)

- Procurement and material inspection tracking (MARs, POs, ETAs)

- OBG prefabrication progress (workshop fabrication, painting, dispatch)

- Civil foundation readiness and interface alignment

- Construction execution strategy, manpower, lifting, PTW, and HSE

- Identification of pending approvals and interface risks

d. Mecton/OBG Management Clarification

- Don Saman responds to clarify internal responsibility:

  - Biju Jose (PM) is on leave until the 20th

  - Ashwin John is designated as the interim focal point from the Mecton/OBG side until the PM returns

- This ensures continuity of communication and accountability during the accelerated phase.

4. Key Themes & Implications

- Strong emphasis from Altrad on governance, control, and visibility

- Clear expectation of discipline in reporting and interface management

- Recognition of live gas plant constraints, driving the need to:

  - Minimize site fabrication

  - Complete as much work as possible at the OBG workshop

- Temporary delegation of authority within Mecton/OBG formally acknowledged and accepted.

5. Outcome / Current Status

- Reporting responsibility and focal points are formally aligned on both sides

- Mecton/OBG is obligated to:

  - Submit the consolidated status report by the stated deadline

  - Maintain daily reporting cadence

- Ashwin John acts as the official interim project interface until the PM’s return.

If you want, I can also:

- Extract contractual risk signals from this email,

- Map this trail against delay / claims exposure, or

- Convert Altrad’s reporting request into a ready-to-use status report template aligned with their expectations.