Below is a concise, structured summary of the Email_06 communication trail, focusing on intent, responsibilities, and key actions.

Summary – Email_06: “SDV New Buildings – Project Focal”

Context & Purpose
The email chain formalizes project communication lines and reporting expectations for the FMP-2277 – PRFEBA Buildings Package (Mess Hall and G+1 Office Building) at Dolphin Energy, under an accelerated execution environment within a live gas plant.

Key Developments

- Change of Focal Point (Altrad Babcock):
Abdul Basit informs all parties that Raheel Babar is appointed as the site focal person for all subcontract operational performance and future correspondence with Mecton / OBG.

- Reporting & Governance Requirements:
Raheel Babar issues a detailed directive requesting a comprehensive, structured project status report covering:

  - Engineering deliverables (Civil, Structural, Arch, MEP, FF, IFCs, MS, ITPs, TQs)

  - Procurement, MARs, inspections, POs, and delivery ETAs

  - OBG prefabrication progress (workshop fabrication, NDT, painting, dispatch, installation sequencing)

  - Civil foundations readiness and interface compliance

  - Execution strategy, look-ahead plans, manpower/equipment, lifting, logistics, HSE/PTW

  - Mandatory daily progress reporting and clear interface issue tracking

  - Submission deadline: Initial consolidated report by COB 8 Oct 2025, followed by daily reports

- Mecton / OBG Response & Continuity:
Don Saman clarifies that Biju Jose (PM) is on vacation until the 20th, and Ashwin John will act as the interim focal point from the Mecton-OBG side to ensure continuity and compliance during this period.

Overall Tone & Implications

- Strong emphasis on technical transparency, tight controls, and schedule adherence

- Clear escalation and governance structure to manage interfaces and risks in a live plant

- Immediate operational accountability placed on the interim focal to meet accelerated milestones